## Dashboard
LFI PORTFOLIO DASHBOARD
Week ending Thursday 16 July 2026 · Reveshnee Gajadhar · Strategic Accounts
📊 PORTFOLIO HEALTH
ACTIVE CLIENTS 14 | ON TRACK 3 | WATCH 3 | AT RISK 3 |  | DONE 3 | NEW 2
🎯 TOP FOCUS THIS WEEK |  |  | ⚠️ AT-RISK SPOTLIGHT
1. [Venu] Reply to Mike re retaining Stefan — outstanding since 9 Jul (Tiger Brands) |  |  | Travel IT | At Risk | Go-live postponed to week of 22 Jul. 3 APIs outstanding, Phase 2 scope undefined.
2. URGENT: Chase Praveen before PRASA RFQ closes Fri 17 Jul (BCX/Nedbank) |  |  | BCX/Nedbank | At Risk | PRASA RFQ closes Fri 17 Jul, Praveen silent since 9 Jul.
3. [Venu] Sign-off on R&P workshop scheduling (CipherWave) |  |  | Tiger Brands | At Risk | TCoE paused. Stefan retention reply sitting with Venu since 9 Jul.
4. [Venu] Resource redeployment decision + Phase 2 scope (Travel IT)
5. Chase Destiny Global directly — JPC RFQ has gone quiet since 17 Jun

## Weekly Snapshot
LFI CLIENT TRACKER ¦ WEEKLY SNAPSHOT
Reveshnee Gajadhar · Strategic Accounts · Week ending Thursday 16 July 2026
TOTAL 14 | ON TRACK 3 | WATCH 3 | AT RISK 3 | DONE 3 | NEW 2 | 🎯 TOP FOCUS THIS WEEK 1. [Venu] Reply to Mike re retaining Stefan — outstanding since 9 Jul (Tiger Brands) 2. URGENT: Chase Praveen before PRASA RFQ closes Fri 17 Jul (BCX/Nedbank) 3. [Venu] Sign-off on R&P workshop scheduling (CipherWave) 4. [Venu] Resource redeployment decision + Phase 2 scope (Travel IT) 5. Chase Destiny Global directly — JPC RFQ has gone quiet since 17 Jun
# | Client | Engagement Type | Health | Key Contact | This Week's Update | Next Action / Decisions | Owner
1 | Travel IT | Multi-Domain Travel Packaging Front-End | At Risk | Murali / Sharmidha / Philip Katz | BRS still unsigned — scope creep risk persists. Phase 1 go-live postponed from 15 Jul to week of 22 Jul: 3 APIs still outstanding (Cancel, Payment Redirect, Itinerary Retrieval). Internal meeting held 15 Jul (Venu, Sharmidha, Phoenix). Phase 2 scope currently undefined, discovery workshops required. | • [Venu] Decision on resource redeployment for idle team members • [Venu] Phase 2 scope / discovery workshop planning • Murali to confirm Phase 1 closure + share Phase 2 decisions next week • Dev team to estimate remaining Phase 1 items for Phase 2 carryover | Reveshnee / Venu
2 | BCX / Nedbank (PRASA) | Cloud Engineering Proposal + PRASA RFQ | At Risk | Ranjith Naidu / Praveen Ponnam | Two proposal revisions sent to Ranjith (9 Jul). PRASA RFQ closes Friday 17 July — Praveen has not responded as at today. Genuine risk of missing the close. | • URGENT: Chase Praveen before Fri 17 Jul close • [Venu] Escalation support if no response by tomorrow morning | Reveshnee
3 | Tiger Brands | TCoE + UiPath RPA POC + EDMS | At Risk | Mike (Architecture) / Chris Lacy / Eugene | TCoE paused client-side since late June — Mike said he'll reach out when ready. EDMS v2.0 sent to Chris Lacy 24 Jun, no response since. Mike asked to retain Stefan on the team; forwarded to Venu on 9 Jul, still awaiting Venu's reply back to Mike. | • [Venu] Reply to Mike directly re retaining Stefan — outstanding since 9 Jul • Monitor Chris Lacy for EDMS v2.0 response • Eugene session (offered free testing to rebuild momentum) — confirm outcome | Reveshnee / Venu
4 | CipherWave | Phase 1 Support + Odoo v19 Upgrade | Watch | Emilie Al-Halaseh / Casper | June hours closed clean: 104hrs, 99 billed after 5hr discount (Venu-approved). Now mid-scope on Odoo v19 upgrade — Emilie met with team, defined 6 requirements, ERD confirmed top priority. Srinivas K drafting formal proposal, due Fri 17 Jul. R&P workshops (2-3 sessions) still awaiting Venu sign-off before scheduling with Emilie. Phase 1.5 scope still overdue from Emilie's side. | • [Venu] Sign-off on R&P workshop scheduling — outstanding • Chase Srinivas K for July support hour estimates (69hr budget, 12 used) • Coordinate team for 5 CW deliverables (ERD, handover docs, env docs, backend code, estimates) • Chase Emilie for overdue Phase 1.5 scope | Reveshnee / Venu
5 | MultiChoice | Staff Aug + SEO + Training | Watch | Thami / Tavish / Sipokazi | Prajwala salary issue resolved via Venu. Thami's role clarity sorted (5 Jul); Thami and Tavish both in Sudhakar's GFO training group. Thami's contract remains parked pending Sipokazi's confirmation of April/May POs. | • Contracting parked — awaiting Sipokazi PO confirmation • Monitor GFO training progress | Reveshnee
6 | Burgess | Odoo Implementation | Watch | Prince / Michelle Badenhorst | BRS signed off by Prince (1 Jul) — major milestone. Awaiting client direction on next phase. Chasing Hartaj re quotation expiry extension; checking MSA status with Michelle. | • Follow up Hartaj re quotation extension • Confirm MSA status with Michelle • Await client direction on next phase | Reveshnee
7 | Zoom Fibre | FlexISP Implementation (CR-003) | Done | Bilaal / Moeen / Pooja | Fully resolved. CR sheet and commercials finalised, Venu sign-off completed 5 Jul after carrying 3 weeks. Quotation sent to Moeen 3 Jul; awaiting his response now. | • Monitor Moeen response to quotation | Reveshnee
8 | Agrément SA | Digitalisation RFQ (36-month) | Done | Prince (internal) / Agrément SA procurement | RFQ finalised with Prince, APA documents signed off, submitted 15 Jul at 12:06pm — ahead of the 12pm-that-day deadline pressure. Closed out cleanly. | • Await outcome | Reveshnee / Prince
9 | Postbank RFP | RFP No. 03/08/25-26 ICT Panel | Done | Vusi Maditsi | DocuSign signed by Venu, submitted to Vusi 23 Jun. Awaiting Postbank outcome. | • Await outcome | Reveshnee / Venu
10 | VMCH / Varsha | Website + Scorecard Phase 1 | On Track | Varsha / Wama | Successful demo delivered. Recurring Friday 11am cadence established with Wama's team — this week's session moved to Fri 17 Jul. | • Standing Friday cadence — track weekly | Reveshnee
11 | ATISA | Ongoing Engagement | On Track | ATISA | Standard monthly process continues. No exceptions raised. | • No action; standard process | Reveshnee
12 | Irdeto | SF Support + Platform POC | On Track | Corne / Detleena | Ongoing SF support continues. Om/Detleena scoping call still to be arranged. | • [Venu] Confirm Om's scoping authority • Schedule Om/Detleena call | Venu / Om
13 | JPC / Destiny Global | Digital Property Asset Register RFQ | New | Margaret (Destiny Global) | Submitted 17 Jun. No word since — has gone quiet for close to a month. Worth a direct nudge rather than continuing to wait. | • Chase Destiny Global directly for status | Reveshnee
14 | Isinkwa Bakery | Odoo Proposal (ad-hoc) | New | Isinkwa Bakery | Proposal sent by Thulane 2 Jul. Awaiting client feedback. | • Await client response | Thulane / Reveshnee

## Proposals Pipeline
PROPOSALS PIPELINE ¦ COMMERCIAL VIEW
As at Thursday 16 July 2026 · Active opportunities across portfolio
Client | Opportunity | Value (ZAR) | Stage | Next Action | Owner
CipherWave | Odoo v19 Upgrade | ~1 month effort (TBC value) | Proposal Shared | Srinivas K drafting formal proposal, due Fri 17 Jul. | Reveshnee / Srinivas K
CipherWave | Phase 1.5 Implementation | R828,857 | On Hold | Scope still overdue from Emilie since end June. | Reveshnee
BCX | Nedbank Cloud Engineering | TBC | Proposal Shared | Two revisions sent to Ranjith 9 Jul. | Reveshnee / Michelle
BCX/Nedbank | PRASA RFQ (subcontractor) | TBC | Submitted | Closes Fri 17 Jul. Awaiting Praveen response. | Reveshnee
Tiger Brands | EDMS v2.0 (Albany Doc Approval) | Pricing pending | Proposal Shared | Sent to Chris Lacy 24 Jun, no response since. | Reveshnee / Rushana
Tiger Brands | TCoE + UiPath RPA | TBC | On Hold | Paused client-side. | Reveshnee / Venu
Agrément SA | Digitalisation RFQ (36-month) | TBC | Submitted | Submitted 15 Jul ahead of deadline. | Reveshnee / Prince
JPC / Destiny Global | Digital Property Asset Register | R453,600 | Submitted | Gone quiet since 17 Jun — needs a direct nudge. | Reveshnee
Isinkwa Bakery | Odoo Proposal | TBC | Proposal Shared | Sent 2 Jul, awaiting feedback. | Thulane
Postbank | RFP No. 03/08/25-26 ICT Panel | TBC | Submitted | Awaiting Postbank outcome since 23 Jun. | Reveshnee / Venu