## Monthly Summary
LFI MONTHLY REVIEW · JUNE 2026
Reveshnee Gajadhar · Strategic Accounts · Month end: 30 June 2026
PORTFOLIO AT A GLANCE
Client | Status | This Month | What I Need
CipherWave | Watch | BCC hours dispute resolved (99hrs billed after 5hr discount). Governance protocols embedded. R&P demo held. Production deliveries held pace despite dispute. | Sign-off on additional 5hr R&P discount
Travel IT | At Risk | Murali escalation contained (11 Jun). Sharmida alignment call held. Phased go-live proposed for July. BRS still unsigned; 3 APIs outstanding. | Approval on flagged Sharmida item
Tiger Brands | At Risk | TCoE stalled — Mike declined biweekly (25 Jun). EDMS v2.0 delivered to Chris Lacy in under 24 hours after revival request. | None urgent
MultiChoice | Watch | MSA v4 signed and sent. Wiseman + Venu client meeting held 27 Jun. Prajwala salary issue raised end of month; being managed. | None urgent
BCX | Watch | Sudhakar Data/AI Architect proposal (v1.0 → v2.0 with signature page) delivered within 48 hours of BCX request. FY27 renewal still on hold. | Venkata renewal decision
Zoom Fibre | At Risk | Technical work complete (Plan IDs, Credit Note, churn fix). CR-003 sign-off carried 3 weeks blocking production deployment. New payment term accepted by Bilaal. | CR + commercials sign-off URGENT
Burgess | Watch | Workshops 4 + 5 attended. Effort estimation sent to Michelle. BRS discussion held end of month (signed 1 Jul). | None urgent
ATISA | On Track | Standard monthly DAC process. No exceptions. | None
VMCH / Varsha | Watch | Quiet month. Wama still resolving website access + branded email 550 error. | None urgent
Irdeto | On Track | Ongoing SF support. Om / Detleena scoping call still to arrange. | Confirm Om's scoping authority
Postbank RFP | Done | DocuSign signed 23 Jun after week's delay; submitted to Vusi. Awaiting Postbank outcome. | None
JPC / MTC RFQ | New | New RFQ received 15 Jun. Two solutions scoped. Proposal submitted to Destiny Global 17 Jun (deadline met). R453,600 Solution A value. | None
Prajwala / Internal HR | New | Salary issue flagged 29 Jun (15% bonus unpaid by India HR/finance). Managed through Tavish + Venu. | None urgent (resolved 3 Jul)
WINS THIS MONTH
1. Postbank RFP closed after signature delay — Venu signed 23 Jun, submitted same day.
2. CipherWave governance reset (10 Jun) landed and held all month.
3. TB EDMS v2.0 turned around in under 24 hours when Chris Lacy revived it.
4. BCX Sudhakar Data/AI Architect proposal shipped in 48 hours (v1.0 → v2.0).
5. CipherWave production deployments held pace despite active client dispute.
RISKS CARRYING INTO NEXT MONTH
1. Travel IT: BRS still unsigned + 3 APIs outstanding + phased go-live hard deadline 15 Jul.
2. CipherWave: Phase 1.5 scope from Emilie overdue; R&P workshops pending Venu sign-off.
3. Zoom Fibre: CR sign-off carried 3 weeks blocking production (resolved 5 Jul).
PRIORITIES FOR NEXT MONTH
1. Travel IT go-live decision by 15 Jul (hard deadline).
2. CipherWave formal v19 upgrade proposal to Emilie.
3. Structural fix for Venu sign-off bottleneck (CR-003 pattern recurring).

## Financial Detail
FINANCIAL DETAIL · June 2026
Michelle input space · Light-gold cells are inputs · Revenue and Outstanding auto-calculate
Client | Hours Utilised | Rate/hr (ZAR) | Revenue Recognised | Invoiced | Paid | Outstanding
CipherWave
Travel IT
Tiger Brands
MultiChoice
BCX
Zoom Fibre
Burgess
ATISA
VMCH / Varsha
Irdeto
Postbank RFP
JPC / MTC RFQ
Prajwala / Internal HR
TOTAL